## 0. Cost Summary
DECISION NEEDED — CEO ACTION REQUIRED
Proposed by: Nghia-VanTrong ¦ Date: 2026-06-28 ¦ For review: CEO & Chairman
Approve Business Premium? | YES — recommended. $22/user/mo (+$9.50 over today). Bundles Win Pro + Intune + Entra P1 + Defender EDR. No servers, no separate AV or MDM license.
Full SSO for GitHub? | OPTIONAL. +$21/user/mo (Enterprise Cloud). Skipping = enforce 2FA only — same security, no SAML convenience.
Full SSO for Bitwarden? | OPTIONAL. +$6/user/mo (Enterprise). Skipping = Teams $3 works, no Entra single sign-on.
Cost impact (20 people) | Premium only: ~$630/mo ¦ Premium + full SSO: ~$1,030/mo ¦ Today: ~$330/mo ¦ Per user: $29 = M365 $22 + GitHub $4 + Bitwarden $3
Risk if NOT acting | Unencrypted laptops + no central login + no EDR = one breach exposes everything. Breach recovery (legal, downtime, lost clients) costs 10-100× more than $300/mo. This proposal closes critical gaps now at minimum spend.
COST BREAKDOWN — how we get to those numbers
Item | Today | Scenario A: Premium only (rec.) | Scenario B: Premium + full SSO
M365 | $12.50 (Standard) | $22.00 (Premium) | $22.00 (Premium)
GitHub | $0 / $4 (Team) | $4.00 (Team — 2FA enforced) | $21.00 (Enterprise — SAML SSO)
Bitwarden | $0 none | $3.00 (Teams — no SSO) | $6.00 (Enterprise — Entra SSO)
Cloudflare Zero Trust | $0 | $0 (≤50 users) | $0 (≤50 users)
TOTAL / USER / MO | ~$12.50 - $16.50 | $29.00 | $49.00
SHARED (split across team):
Item | Cost | Note
Monitoring / SIEM hosting | ~$15-40/mo | Wazuh + Grafana on EC2 t3.small
AWS backup storage | ~$5-30/mo | S3 snapshots
Domain + DNS | ~$1/mo | ~$10-20/yr at Cloudflare/Namecheap
SHARED TOTAL / MO | ~$21-71/mo
ONE-TIME / CAPITAL:
Item | Cost | Note
Win 11 Pro (if NOT going Premium) | $99 / laptop | Skip — included in Premium
New laptop per hire | ~$600-1,200 | Business-grade, TPM 2.0
Office router + Wi-Fi | ~$200-800 | UniFi / Firewalla / Meraki
NAS (future) | ~$300-800 + disks | Not needed now
20-PERSON EXAMPLE:
| Scenario A — recommended | Scenario B — full SSO
Per-user monthly | $29 x 20 = $580/mo | $49 x 20 = $980/mo
Shared infra | ~$30-50/mo | ~$30-50/mo
TOTAL / MONTH | ~$610-630/mo | ~$1,010-1,030/mo
TOTAL / YEAR | ~$7,320-7,560/yr | ~$12,120-12,360/yr
Delta vs. Today (~$330/mo) | +$280-300/mo | +$680-700/mo
IMPLEMENTATION PHASES (estimated — 20-person company):
Phase | What | Target timeline | Cost impact
Phase 1 — Foundation | Business Premium upgrade + Win Pro Entra enroll + MFA + BitLocker + AppLocker + Cloudflare Zero Trust + Bitwarden Teams | Weeks 1-4 | ~$630/mo from day 1 (Scenario A)
Phase 2 — Hardening | Intune full MDM + Conditional Access + Defender tuning + Wazuh SIEM + offboarding automation + agent/app development | Months 2-3 | Included in Scenario A
Phase 3 — Full SSO (optional) | GitHub Enterprise SAML + Bitwarden Enterprise Entra SSO + SCIM auto-provisioning for all apps | Month 4+ — requires CEO approval | ~$1,030/mo (Scenario B)

## 1. Proposal
ENTERPRISE IT PROPOSAL — what we set up + how ¦ Proposed by: Nghia-VanTrong ¦ 2026-06-28
See '0. Cost Summary' tab for the recommendation, pricing, and the one big decision.
This table covers all 26 capability areas: what each rule does, the free way to enforce it, and the cheapest viable path.
# | What we set up | Strict rule (user experience) | Free way | Paid upgrade (price) | We recommend
1 | Central login / SSO | One company account for Windows + M365 + GitHub + tools. No personal accounts. | Entra ID Free | Entra P1 (in Premium $22/user) | Free now
2 | MFA everywhere | Every login needs phone approval | Security Defaults | Conditional Access (Premium) | Free now
3 | Disk encryption | Laptop drive encrypted; lost laptop = safe | BitLocker + Entra escrow | — | Free
4 | Antivirus / EDR | Real-time AV + central threat view | Windows Defender | Defender for Business (in Premium) / Sophos ~$3-4 / SentinelOne ~$5-7 | Defender for Business via Premium
5 | Web filtering | Internet blocked by default; only approved sites open; user requests to unblock | Cloudflare Zero Trust (free ≤50 users) | Cloudflare paid | Cloudflare Free
6 | Software control | Only approved apps run; unknown .exe blocked; user requests to install | AppLocker (needs Win Pro) | WDAC + Intune (Premium) | AppLocker now
7 | No local admin | Users can't install/change system; admin per-request | Remove from Administrators | Intune LAPS (Premium) | Free now
7b | Temporary admin (1h install window) | User requests install → manager approves → gets local admin for 1 hour → auto-revoked. No permanent admin rights. | Windows LAPS (built-in Win 11 22H2+): IT shares rotating local admin password for session; password auto-rotates after use | Self-built app + Intune (Premium): approve request → Intune script grants local admin → auto-revokes after 1h | Windows LAPS now → Intune automation via Premium
8 | No USB storage | USB drives blocked (stops data leaks) | Group Policy (Win Pro) | Intune (Premium) | Free now
9 | Forced updates | Users can't skip security patches | Windows Update for Business | Intune rings (Premium) | Free now
10 | Device management | Push policy / remote wipe to all laptops | Manual per-laptop | Intune MDM (in Premium) | Manual now → Intune via Premium
11 | Email security | Anti-phishing, safe links/attachments | EOP (in M365) | Defender for Office (Premium) | Free now
12 | Password manager | Shared vault for keys; no password reuse | Bitwarden Free | Bitwarden Teams $3 (no SSO) / Enterprise $6 (Entra SSO) | Teams (Enterprise if SSO required)
13 | Logging / monitoring | Central logs of sign-ins + threats | Entra logs + Wazuh (free) | Paid SIEM | Free SW + ~$15-40/mo hosting
14 | Offboarding | Exit = instant account disable + device wipe | Entra (free) | + Intune wipe | Free now → Intune
15 | AWS account security | Root locked + MFA, IAM least-privilege, GuardDuty alerts, billing alarm, Secrets Manager | AWS IAM + MFA + budget alerts (free) | GuardDuty / Security Hub (usage-based) | Free basics now
16 | Code & secrets security | No passwords/keys in code; auto-scan repos; dependency alerts | GitHub secret scanning + Dependabot (free) | GitHub Advanced Security | Free
17 | Backup & disaster recovery | DB + tool data backed up daily, tested restore | AWS automated snapshots + OneDrive (free-ish) | AWS Backup / cross-region | Snapshots now
18 | Mobile / email on phones | Company email on phone needs PIN + remote wipe | Entra mobile app protection (basic, free) | Intune MAM (Premium) | Free now → Intune
19 | Network / remote access | Secure access to internal tools; no open ports | Cloudflare Access (free ≤50) / VPN | Cloudflare paid / AWS VPN | Cloudflare Access (free)
20 | Security awareness | Staff trained + phishing tested | Free training + manual phishing test | Attack Simulation (Premium) / KnowBe4 | Free now → Premium sim
21 | Incident response | 1-page plan: lost laptop / breach / leaked key | Written runbook (free) | — | Free — write it
22 | Vulnerability scanning | Agent scans every laptop/server for known CVEs (the FPT 'scan' app) | OpenVAS / Nessus Essentials (free, limited) | Defender Vuln Mgmt (in Premium) / Tenable / Qualys | Defender VM via Premium
23 | Endpoint DLP + data labeling | Block copy/email/upload of sensitive data; label files Confidential (FPT Trellix DLP) | M365 Purview basic DLP (email/SharePoint) | Purview Endpoint DLP (Premium/E5 add-on) | Email DLP now → Endpoint DLP later
24 | CASB / SaaS control | See & control which cloud apps staff use; block risky SaaS (shadow IT) | Cloudflare CASB (basic) | Defender for Cloud Apps (E5) | Cloudflare/manual now
25 | Device certificates (802.1X) | Only company devices (with cert) join Wi-Fi/VPN | Manual certs (free) | Intune SCEP/PKCS auto-deploy (Premium) | Manual now → Intune
26 | Network access control (NAC) | Only compliant/healthy devices get on the network | Conditional Access device compliance (P1) | NAC appliance (Cisco ISE etc.) | Conditional Access via Premium

## 2. System & Cost
SYSTEM-BY-SYSTEM PLAN + COST (today → enterprise+SSO target)
CEO requirement: ONE Entra login (AD SSO) for everything.
System | Today | Enterprise + SSO target | Upgrade needed | Cost | SSO?
Windows laptops | Win Home, local accounts | Win Pro + Entra Join (login = company account) | Win 11 Pro (or get via Premium) | $99 once/laptop | SSO $0
M365 (Outlook/Teams/OneDrive) | Business Standard | Keep + add central mgmt & EDR | Business Premium (recommended) | +$9.50/user/mo | SSO $0 (native)
Entra ID (identity core) | Free | SSO + MFA now; Conditional Access + SCIM provisioning | Entra P1 (comes in Premium) | in Premium | —
AWS console | root + IAM | Login with Entra (IAM Identity Center) | Config only | $0 | SSO $0
GitHub | Free / Team | SAML SSO for all devs | GitHub Enterprise Cloud (Team/Free can't SAML) | $21/user/mo | SSO = paid
Bitwarden | none / Teams | Login with Entra | Bitwarden Enterprise (Teams has no SSO) | $6/user/mo | SSO = paid
Cloudflare | none | Default-deny web filter + Entra SSO (Access) | Config only | $0 (≤50 users) | SSO $0
Self-built tools | own login | 'Login with Microsoft' (Entra OIDC) | Dev work per tool | $0 + dev time | SSO $0
Antivirus / logging / encryption | none / partial | Defender + Wazuh + BitLocker + AppLocker | Config only (needs Win Pro) | $0 | —
Laptop hardware | existing laptops | Business-grade laptop w/ TPM 2.0 per employee | Buy per new hire | ~$600-1,200 once/laptop | —
Office network | consumer router | Firewall/router + managed Wi-Fi (segmented, guest VLAN) | UniFi / Firewalla / Meraki | ~$200-800 once + opt. license | —
Company domain + DNS | domain owned | Domain + DNS (email records, internal tools) | Registrar (Cloudflare/Namecheap) | ~$10-20/yr | —
Monitoring / SIEM hosting | none | Wazuh + Grafana on a small AWS instance | AWS EC2 t3.small + storage | ~$15-40/mo | —
Backup storage | OneDrive included | DB snapshots + cross-region backup | AWS Backup / S3 | usage (~$5-30/mo) | —
Mobile phones | personal phones | Email on phone w/ PIN + remote wipe | BYOD (Entra/Intune MAM) | $0 (Intune in Premium) | SSO $0
Security awareness training | none | Annual training + phishing simulation | Free / KnowBe4 | $0-2/user/mo | —
See '0. Cost Summary' tab for the full decision summary and cost breakdown.

## 3. Appendix
APPENDIX A — OFFICE / ON-PREM INFRASTRUCTURE: do we need a physical server?
Short answer: NO traditional server now — Entra ID (cloud) replaces on-prem AD.
Plan a NAS for local backup later; a small server ONLY if accounting/HR app needs a LAN database.
Item | Need it now? | Cloud-native way (recommended) | If on-prem instead | Verdict
Domain controller / AD server | No | Entra ID = cloud directory, replaces on-prem AD | Windows Server + AD (cost + admin) | Skip — use Entra
Asset mgmt (PC/printer inventory) | Optional | Intune (Premium) or your self-built asset tool | Lansweeper on a server | Self-built / Intune
File server (user documents) | No | SharePoint / OneDrive (in M365) | File server box | Cloud
NAS (local backup + bulk files) | Future (recommended) | AWS = offsite copy; NAS = local 3-2-1 copy + fast LAN files | NAS + disks | Add later ~$300-800 + disks
Printers | Yes (hardware) | Universal Print (cloud, in Premium) or direct network printers | Print server | Network printers
Department PCs (HR, accounting) | Manage like laptops | Entra Join + same policies/agents | — | Same as laptops
Accounting/HR LAN app (MISA, FAST...) | If used | Use cloud version if available | Small local SQL server/VM | FLAG — may need 1 local server
Local backup target | Future | AWS Backup (offsite) | NAS (local) | NAS later for 3-2-1
RECOMMENDATION: Stay cloud-native now (no server). Budget a NAS later for local backup + bulk storage.
Only buy a physical server if your accounting/HR software requires an on-LAN database.
APPENDIX B — DEVICE TRACKING & ASSET MANAGEMENT: options + cost
FPT uses on-prem agent model: AD + Group Policy + SCCM/MECM + Trellix ePO. SCCM = on-prem Intune. Overkill for a small company.
You do NOT need Intune to track — just an AGENT reporting somewhere. SCCM (FPT) = Intune (cloud) = your own agent.
Option | What it is | Cost | Best for
A. Your own agent + app | Build agent + dashboard (your current plan) | Dev time + ~$15-40/mo hosting | Full control, custom workflows + tie-in to HR/leave/OT tools
B. Free 3rd-party endpoint tool | ManageEngine Endpoint Central (free ≤25 PCs) / Lansweeper free tier | $0 (small fleet) | Fast start, no building
C. GPO + login scripts | AD/Entra + scripts dump inventory to a share | $0 | Very basic inventory only
D. Intune (cloud SCCM) | Modern cloud MDM, no servers | in Business Premium | Cleanest if going Premium
IF WE BUILD OUR OWN (Option A) — cost breakdown:
Item | Cost | Note
App + agent development | Your dev time (main cost) | Agent collects installed apps, network, hardware, BitLocker status → reports to your API
Hosting (app + DB + API) | ~$15-40/mo | EC2/ECS + RDS + S3 — shares the AWS infra already in the budget
Microsoft Graph API | $0 (in Business Standard) | Standard = basic data only. Installed-apps + compliance + remote wipe need Intune (Premium).
Agent code signing | $0 self-signed OR ~$200-500/yr public cert | So AppLocker/SmartScreen don't block your own agent
Enforcement engine | $0 | Reuse OS-native: AppLocker, GPO, Cloudflare WARP, Defender, BitLocker
KEY: Build = visibility + workflow layer. Buy/configure = enforcement layer underneath.
The app does NOT replace Win Pro / Cloudflare / Defender / Intune — those are the engines it sits on top of.